## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sai Pallav | 2026-01-10 | Large documents were not split correctly, causing retrieval inaccuracies. | Sprint 1 | Sai Pallav | Logic | Implemented fixed chunk size with overlap. | 2026-01-11 | Closed | Verified with sample queries
2 | Sai Pallav | 2026-01-12 | Chatbot returned irrelevant answers for vague user queries. | Sprint 2 | Sai Pallav | Functional | Improved similarity threshold and top-k retrieval logic. | 2026-01-13 | Closed | Retrieval accuracy improved
3 | Sai Pallav | 2026-01-14 | System failed when empty or unsupported documents were uploaded. | Sprint 2 | Sai Pallav | Validation | Added input validation and error handling. | 2026-01-14 | Closed | Edge cases handled
4 | Sai Pallav | 2026-01-14 | Retrieved document chunks were partially irrelevant for some user queries. | Sprint 2 | Sai Pallav | Functional | Adjusted similarity threshold and optimized top-k retrieval logic. | 2026-01-15 | Closed | Retrieval quality improved
5 | Sai Pallav | 2026-01-16 | LLM generated responses without fully using retrieved document context. | Sprint 2 | Sai Pallav | Logic | Updated prompt to enforce context-based answer generation. | 2026-01-17 | Closed | Answers are now context-grounded
6 | Sai Pallav | 2026-01-22 | Chat history was not retained properly when multiple messages were exchanged. | Sprint 3 | Sai Pallav | Functional | Implemented proper message state handling in the front-end. | 2026-01-23 | Closed | Chat flow verified
7 | Sai Pallav | 2026-01-25 | Chatbot failed to respond correctly to follow-up questions due to missing conversation context. | Sprint 3 | Sai Pallav | Logic | Added conversation state management for multi-turn dialogue. | 2026-01-26 | Closed | Context handling improved

## Sheet2
Logical
User Interface
Maintainability
Standards
Others